## Day (1)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-27
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created Product & Sprint Backlog docs |  | Study assignment 8 closer | Time
This form |  | start decomposing Product backlog
Linked in to github - uploaded docs |  | Study calculator online
Discussed roles
Speaker 2 -> | Aaron Elliott
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created link and repositiory in GitHub. Rewatched GitHub checkout video Established two workstations (laptops) for testing. One to do the initial push and commit to GitHub, the other successfully checked out the code remotely and did a successful commit and push. Installed and worked/learned Windows Builder for Eclipse. |  | Answer product questions for client Will look into understanding Scrum Master duties Start on chapter review questions
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created a github account |  | Review swing for java GUI | Work
Chapter review questions |  | Check out windows builder
Get linked to github

## Day (2)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-28
Speaker 1 -> | Mark Erickson
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created List of questions to ask customer |  | Add more to the Sprint Backlog
Reviewed online calculator |  | Test Main.java
created Sprint Planning Meeting Notes
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Did some research online about Scum Master responsibilities. |  | Work on test case for Time class
Finished homework part 1
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Downloaded windows builder to eclipse |  | Look at calculations for calculator
Did a review of java swing |  | Configure eclipse for laptop
Looked at different window layouts for java

## Day (3)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-29
Speaker 1 -> | Mark Erickson
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Add expected classes to sprint backlog |  | Build test case for distance (local)
re-imported git project |  | Work more on part 1
corrected problems with running main.java
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Researched functinality for Time function |  | Start creating intial GUI
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Began looking up calculators for calculator |  | Begin working on pace calculation
Setup eclipse preferences on laptop

## Day (4)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-30
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Worked on part 1 (assign-8) |  | Implement testcase for Distance
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created intial GUI |  | Looking into implementing method for calculating Time | Trying to understand some of the Java syntax to be able to capture data from the text field when a button is pressed.
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Started working on pace calculation |  | Establish calculations and begin building test cases

## Day (5)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-31
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (6)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-01
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (7)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-02
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (8)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-03
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (9)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-04
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (10)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-05
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (11)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-06
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (12)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-07
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (13)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-08
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (14)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-09
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (15)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-10
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?