## Sprint 2
Sprint 2 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
1 | 1 | Remove hours field from pace | 0.5 | ME | 0.5
2 | 2 | remove distance textbox input, make selections the only option | 0.5 | AE | 0.1
1,3 | 3 | Assign error messenges to invalid input | 1 | ME | 1
1 | 4 | pace must display Miles only | 1 | ME | 1
1,3 | 5 | Decimal format for seconds only field 0.1 | 0.5 | AE | 0.3
High
1,3 | 6 | no decimal in minutes or hours | 1 | AE | 0.5
1,2,3 | 7 | Apply checkstyle-clean up code | 5 | SS
1,2,3 | 8 | test GUI | 2 | AE | 3.5
1,2,3 | 9 | Blackbox tests | 3 | SS
1,2,3 | 10 | Freeze window | 0.5 | AE | 0.1
1,3 | 11 | Set user input length for all textfields. | 0.5 | AE | 0.5
1 | 12 | Update UI layout to compensate for textfields that were taken out. | 2 | AE | 0.5
1,2,3 | 13 | Misc UI updates to enhance layout visually?? | 2 |  | 0.2
3 | 14 | Add checks for invalid data | 0.5 | AE | 0.5
1 | 15 | Add checks for invlaid data | 0.5 | ME | 0.5
Medium
2 | 16 | test Distance | 3 | AE | 3
1 | 17 | Test Pace | 3 | ME
3 | 18 | Test Time | 3 | SS
1,2,3 | 19 | Junit test for the Unit Converter class. | 2 | AE
1 | 20 | Consider taking the existing combobox for Pace out. This will have to refactor some code but may be beneficial in long??? | 3 | AE
1,2 | 21 | Check for div by zero | 1 | AE | 2
1,2,3 | 22 | Added logo to the UI | 0.5 | AE | 0.7
|  | Total | 36 |  | 14.9 | 21.1

## Sprint 1
Sprint 1 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
| 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member | 0.5 | Team |  | 2016-11-02
| 2 | Setup GitHub | 0.5 | AE
| 3 | Link to GitHub / Add Backlogs | 0.5 | ME
| 4 | Link to GitHub / (Strike this comment to confirm) | 0.5 | SS
| 5 | Add Prof. to GitHub | 0.5 | AE
| 6 | View Sample website (Review Calculator) | 0.5 | Team
| 7 | Do part 1 of assignment-8 | 2 | Team
3 | 8 | Create testcase for Calculation to compute Time | 1 | AE
2 | 9 | Create testcase for Calculation to compute distance | 1 | ME
1 | 10 | Create testcase for Calculation to compute pace | 1 | SS
| 11 | Build user interface-window.java (Windows Builder) | 3 | AE |  | Update Product Backlog from web
2 | 12 | build Class Distance.java | 1 | ME |  | Next review
1 | 13 | build Class Pace.java | 1 | SS |  | turn in sprint 2 backlog, chart, demo, Junit testing
3 | 14 | build Class Time.java | 1 | SS
4 | 15 | Updated GUI to refereence utility class | 2 | AE |  | UML 10
4 | 16 | Updated GUI for correct calculations | 2 | AE
17
|  | Total | 18
Submit other artifact separately
Zip only eclispe files
Use-cases

## Burndown Chart
Date | Remaining | Complete
2016-11-02 | 36 | --
2016-11-03 | 29 | 7 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-11-04 | 23 | 6 | 2 | Setup GitHub
2016-11-05 | 18.5 | 4.5 | 3 | Link to GitHub / Add Backlogs
2016-11-06 | 15 | 3.5 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-11-07 | 15 | 0 | 5 | Add Prof. to GitHub
2016-11-08 | 15 | 0 | 6 | View Sample website (Review Calculator)
|  | 0 | 7 | Do part 1 of assignment-8(research)
|  |  | 8 | Create testcase for Calculation to compute Time
|  |  | 9 | Create testcase for Calculation to compute distance
|  |  | 10 | Create testcase for Calculation to compute pace
|  |  | 11 | Build user interface-window.java (Windows Builder)
|  |  | 12 | build Class Distance.java
|  |  | 13 | build Class Pace.java
|  |  | 14 | build Class Time.java