## Sprint 1
Sprint 1 Backlog
| Item # | Description | Est | By
Very High
| 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member | 0.5 | Team
| 2 | Setup GitHub | 0.5 | AE
| 3 | Link to GitHub / Add Backlogs | 0.5 | ME
| 4 | Link to GitHub / (Strike this comment to confirm) | 0.5 | SS
| 5 | Add Prof. to GitHub | 0.5 | AE
| 6 | View Sample website (Review Calculator) | 0.5 | Team
| 7 | Do part 1 of assignment-8 | 2 | Team
| 8 | Create testcase for Calculation to compute Time | 1 | AE
| 9 | Create testcase for Calculation to compute distance | 1 | ME
| 10 | Create testcase for Calculation to compute pace | 1 | SS
| 11 | Build user interface-window.java (Windows Builder) | 3 | AE
| 12 | build Class Distance.java | 1 | ME
| 13 | build Class Pace.java | 1 | SS
| 14 | build Class Time.java | 1 | AE
15
16
17
|  | Total | 14

## Burndown Chart
Date | Remaining | hrs
2016-10-26 | 14
2016-10-26 | 13.5 | 0.5 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-10-26 | 13 | 0.5 | 2 | Setup GitHub
2016-10-26 | 12.5 | 0.5 | 3 | Link to GitHub / Add Backlogs
2016-10-27 | 12 | 0.5 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-10-27 | 11.5 | 0.5 | 5 | Add Prof. to GitHub
2016-10-27 | 11 | 0.5 | 6 | View Sample website (Review Calculator)
2016-10-28 | 9 | 2 | 7 | Do part 1 of assignment-8(research)
2016-10-30 | 8 | 1 | 8 | Create testcase for Calculation to compute Time
2016-10-30 | 7 | 1 | 9 | Create testcase for Calculation to compute distance
2016-10-30 | 6 | 1 | 10 | Create testcase for Calculation to compute pace
2016-10-31 | 3 | 3 | 11 | Build user interface-window.java (Windows Builder)
2016-11-01 | 2 | 1 | 12 | build Class Distance.java
2016-11-01 | 1 | 1 | 13 | build Class Pace.java
2016-11-01 | 0 | 1 | 14 | build Class Time.java