## Day (1)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-27
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created Product & Sprint Backlog docs |  | Study assignment 8 closer | Time
This form |  | start decomposing Product backlog
Linked in to github - uploaded docs |  | Study calculator online
Discussed roles
Speaker 2 -> | Aaron Elliott
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created link and repositiory in GitHub. Rewatched GitHub checkout video Established two workstations (laptops) for testing. One to do the initial push and commit to GitHub, the other successfully checked out the code remotely and did a successful commit and push. Installed and worked/learned Windows Builder for Eclipse. |  | Answer product questions for client Will look into understanding Scrum Master duties Start on chapter review questions
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created a github account |  | Review swing for java GUI | Work
Chapter review questions |  | Check out windows builder
Get linked to github

## Day (2)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-28
Speaker 1 -> | Mark Erickson
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created List of questions to ask customer |  | Add more to the Sprint Backlog
Reviewed online calculator |  | Test Main.java
created Sprint Planning Meeting Notes
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Did some research online about Scum Master responsibilities. |  | Work on test case for Time class
Finished homework part 1
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Downloaded windows builder to eclipse |  | Look at calculations for calculator
Did a review of java swing |  | Configure eclipse for laptop
Looked at different window layouts for java

## Day (3)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-29
Speaker 1 -> | Mark Erickson
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Add expected classes to sprint backlog |  | Build test case for distance (local)
re-imported git project |  | Work more on part 1
corrected problems with running main.java
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Researched functinality for Time function |  | Start creating intial GUI
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Began looking up calculators for calculator |  | Begin working on pace calculation
Setup eclipse preferences on laptop

## Day (4)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-30
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Worked on part 1 (assign-8) |  | Implement testcase for Distance
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created intial GUI |  | Looking into implementing method for calculating Time | Trying to understand some of the Java syntax to be able to capture data from the text field when a button is pressed.
Speaker 3 -> | Samuel Scheitlin
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Started working on pace calculation |  | Establish calculations and begin building test cases

## Day (5)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-10-31
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Worked on test cases |  | standardize code
add test cases provided by client
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Updated GUI to pass user inputs into the utility classes. Add intial calulations on the back end to have necssary output. |  | Continue to make modifications to the GUI. | Some bugs within the software, some UI outputs are not correct.
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (6)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-01
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
removed hungarian notation |  | Created burndown chart
Added test cases provided by client |  | review math formulas
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Continued working on UI. Updated Unit Conversion class to perform calculations for hours, minutes, and seconds. |  | Will correspond with group for preparations for Sprint 1 review.
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (7)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-02
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Created burndown chart |  | Try to get PaceCalculator to work with window builder
review math formulas |  | rename version that doesn't work
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Prepare and particpate in Sprint 1 review. |  | Sprint 2 planning
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (8)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-03
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Renamed PaceCalculator that didn't have design tab |  | Refine Backlogs and burndown chart from class discussion
Copied functionality from V1 to new PaceCalculator |  | Review checkstyle & PaceCalculator
Add some limits to the input fields then merge them if someone has made changes to PaceCalculator
Speaker 2 -> | Aaron
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Sprint 2 planning |  | Updated code to do checks for invalid user input.
Disabled visibility for distance textfield and combobox for kilometers and miles.
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (9)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-04
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Had computer difficulties |  | Refine Backlogs and burndown chart from class discussion
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Added to UI layout (logo) |  | Test and correct discovered bugs
Testing calculations and UI |  | Add checks to invalid input
Corrected in code division by zero
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (10)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-05
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Had computer difficulties |  | Refine Backlogs and burndown chart from class discussion
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Disabled user input for distance field |  | Checkstyle to main class
Changed unit conversion methods to from String to double |  | Testing
Added label to UI
Changed size of distance textfield
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (11)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-06
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Refine Backlogs and burndown chart from class discussion |  | GUI testing
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (12)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-07
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
GUI testing |  | Prep backlogs to turn them in.
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (13)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-08
Speaker 1 -> | Mark
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Prep backlogs to turn them in. |  | format artifacts per assignment
assemble assignment requirements
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?

## Day (14)
Daily Scrum Meeting (e-version) |  |  | Date: | 2016-11-09
Speaker 1 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 2 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?
Speaker 3 -> | Put your name in this Cell
What did you do Yesterday? |  | What will you do today? | What obstacles are in your way?