## Sprint 2
Sprint 2 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
| 1 | No hours for pace | 0.5 | ME | 0.5
| 2 | no decimal in minutes or hours | 1 | AE | 0.5
| 3 | remove distance textbox (selection only) | 0.5 | AE | 0.1
| 4 | Mile for pace only | 1 | ME | 1
| 5 | report reason error message appears enter correct units / decimal / char /etc | 1 | ME | 1
| 6 | Check for div by zero | 1 | AE | 2
| 7 | Apply checkstyle-clean up code | 5 | SS
- | - | test GUI | 2 | AE | 3.5
2 | 9 | test Distance | 3 | AE | 3
1 | 10 | Test Pace | 3 | ME |  | Update Product Backlog from web
| 11 | Test Time | 3 | SS
2 | 12 | Blackbox tests | 3 | SS |  | Next review
1 | 13 | Freeze window | 0.5 | AE | 0.1 | turn in sprint 2 backlog, chart, demo, Junit testing
3 | 14 | Decimal format for seconds only field 0.1 | 0.5 | AE | 0.3
4 | 15 | Set user input length for all textfields. | 0.5 | AE | 0.5 | Zip only eclispe files
4 | 16 | Consider taking the existing combobox for Pace out. This will have to refactor some code but may be beneficial in long??? | 3 | AE |  | Submit other artifact separately
| 17 | Junit test for the Unit Converter class. | 2 | AE
|  | Update UI layout to compensate for textfields that were taken out. | 2 | AE | 0.5 | UML 10
|  | Misc UI updates to enhance layout visually?? | 2 |  | 0.2
|  | Added logo to the UI | 0.5 | AE | 0.7
|  | Add checks for invalid data | 0.5 | AE | 1
|  | Add checks for invlaid data | 0.5 | ME | 1
|  | Total | 36 |  |  | Use-cases

## Sprint 1
Sprint 1 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
| 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member | 0.5 | Team
| 2 | Setup GitHub | 0.5 | AE
| 3 | Link to GitHub / Add Backlogs | 0.5 | ME
| 4 | Link to GitHub / (Strike this comment to confirm) | 0.5 | SS
| 5 | Add Prof. to GitHub | 0.5 | AE
| 6 | View Sample website (Review Calculator) | 0.5 | Team
| 7 | Do part 1 of assignment-8 | 2 | Team
3 | 8 | Create testcase for Calculation to compute Time | 1 | AE
2 | 9 | Create testcase for Calculation to compute distance | 1 | ME
1 | 10 | Create testcase for Calculation to compute pace | 1 | SS
| 11 | Build user interface-window.java (Windows Builder) | 3 | AE
2 | 12 | build Class Distance.java | 1 | ME
1 | 13 | build Class Pace.java | 1 | SS
3 | 14 | build Class Time.java | 1 | SS
4 | 15 | Updated GUI to refereence utility class | 2 | AE
4 | 16 | Updated GUI for correct calculations | 2 | AE
17
|  | Total | 18

## Burndown Chart
Date | Remaining | hrs
2016-10-26 | 18
2016-10-26 | 17.5 | 0.5 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-10-26 | 17 | 0.5 | 2 | Setup GitHub
2016-10-26 | 16.5 | 0.5 | 3 | Link to GitHub / Add Backlogs
2016-10-27 | 16 | 0.5 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-10-27 | 15.5 | 0.5 | 5 | Add Prof. to GitHub
2016-10-27 | 15 | 0.5 | 6 | View Sample website (Review Calculator)
2016-10-28 | 13 | 2 | 7 | Do part 1 of assignment-8(research)
2016-10-30 | 12 | 1 | 8 | Create testcase for Calculation to compute Time
2016-10-30 | 11 | 1 | 9 | Create testcase for Calculation to compute distance
2016-10-30 | 10 | 1 | 10 | Create testcase for Calculation to compute pace
2016-10-31 | 7 | 3 | 11 | Build user interface-window.java (Windows Builder)
2016-11-01 | 6 | 1 | 12 | build Class Distance.java
2016-11-01 | 5 | 1 | 13 | build Class Pace.java
2016-11-01 | 4 | 1 | 14 | build Class Time.java
2016-11-02 | 2 | 2
2016-11-02 | 0 | 2