## Sprint 2
Sprint 2 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
| 1 | No hours for pace
| 2 | no decimal in minutes or hours
| 3 | remove distance textbox (selection only)
| 4 | Mile for pace only
| 5 | report reason error message appears enter correct units / decimal / char /etc
| 6 | Check for div by zero
| 7 | Apply checkstyle-clean up code
- | - | test GUI
2 | 9 | test Distance | 3
1 | 10 | Test Pace | 3 |  |  | Update Product Backlog from web
| 11 | Test Time | 3
2 | 12 | Blackbox tests |  |  |  | Next review
1 | 13 | Freeze window |  |  |  | turn in sprint 2 backlog, chart, demo, Junit testing
3 | 14 | Decimal format for seconds only field 0.1
4 | 15 |  |  |  |  | Zip only eclispe files
4 | 16 |  |  |  |  | Submit other artifact separately
17
UML 10
|  | Total | 9 |  |  | Use-cases

## Sprint 1
Sprint 1 Backlog
Product # | Item # | Description | Est | By | Actual
Very High
| 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member | 0.5 | Team
| 2 | Setup GitHub | 0.5 | AE
| 3 | Link to GitHub / Add Backlogs | 0.5 | ME
| 4 | Link to GitHub / (Strike this comment to confirm) | 0.5 | SS
| 5 | Add Prof. to GitHub | 0.5 | AE
| 6 | View Sample website (Review Calculator) | 0.5 | Team
| 7 | Do part 1 of assignment-8 | 2 | Team
3 | 8 | Create testcase for Calculation to compute Time | 1 | AE
2 | 9 | Create testcase for Calculation to compute distance | 1 | ME
1 | 10 | Create testcase for Calculation to compute pace | 1 | SS
| 11 | Build user interface-window.java (Windows Builder) | 3 | AE
2 | 12 | build Class Distance.java | 1 | ME
1 | 13 | build Class Pace.java | 1 | SS
3 | 14 | build Class Time.java | 1 | SS
4 | 15 | Updated GUI to refereence utility class | 2 | AE
4 | 16 | Updated GUI for correct calculations | 2 | AE
17
|  | Total | 18

## Burndown Chart
Date | Remaining | hrs
2016-10-26 | 18
2016-10-26 | 17.5 | 0.5 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-10-26 | 17 | 0.5 | 2 | Setup GitHub
2016-10-26 | 16.5 | 0.5 | 3 | Link to GitHub / Add Backlogs
2016-10-27 | 16 | 0.5 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-10-27 | 15.5 | 0.5 | 5 | Add Prof. to GitHub
2016-10-27 | 15 | 0.5 | 6 | View Sample website (Review Calculator)
2016-10-28 | 13 | 2 | 7 | Do part 1 of assignment-8(research)
2016-10-30 | 12 | 1 | 8 | Create testcase for Calculation to compute Time
2016-10-30 | 11 | 1 | 9 | Create testcase for Calculation to compute distance
2016-10-30 | 10 | 1 | 10 | Create testcase for Calculation to compute pace
2016-10-31 | 7 | 3 | 11 | Build user interface-window.java (Windows Builder)
2016-11-01 | 6 | 1 | 12 | build Class Distance.java
2016-11-01 | 5 | 1 | 13 | build Class Pace.java
2016-11-01 | 4 | 1 | 14 | build Class Time.java
2016-11-02 | 2 | 2
2016-11-02 | 0 | 2